{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["外委"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"外委","index":0,"n_rows":104,"n_cols":6,"rows_kept":104,"merged":[[0,0,0,5],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[4,0,8,0],[4,1,8,1],[4,2,8,2],[4,4,8,4],[4,5,8,5],[9,0,14,0],[9,1,14,1],[9,2,14,2],[9,4,14,4],[9,5,14,5],[16,0,22,0],[16,1,22,1],[16,2,22,2],[16,4,22,4],[16,5,22,5],[23,0,35,0],[23,1,35,1],[23,2,35,2],[23,4,35,4],[23,5,35,5],[36,0,39,0],[36,1,39,1],[36,2,39,2],[36,4,39,4],[36,5,39,5],[41,0,60,0],[41,1,60,1],[41,2,60,2],[41,4,60,4],[41,5,60,5],[62,0,67,0],[62,1,67,1],[62,2,67,2],[62,4,67,4],[62,5,67,5],[68,0,70,0],[68,1,70,1],[68,2,70,2],[68,4,70,4],[68,5,70,5],[71,0,75,0],[71,1,75,1],[71,2,75,2],[71,4,75,4],[71,5,75,5],[76,0,82,0],[76,1,82,1],[76,2,82,2],[76,4,82,4],[76,5,82,5],[83,0,89,0],[83,1,89,1],[83,2,89,2],[83,4,89,4],[83,5,89,5],[90,0,94,0],[90,1,94,1],[90,2,94,2],[90,4,94,4],[90,5,94,5],[95,0,98,0],[95,1,98,1],[95,2,98,2],[95,4,98,4],[95,5,98,5],[99,0,100,0],[99,1,100,1],[99,2,100,2],[99,4,100,4],[99,5,100,5],[101,0,102,0],[101,1,102,1],[101,2,102,2],[101,4,102,4],[101,5,102,5]],"flags":["formulas_cached_only"]}
["2022年春季烧成前系统机械设备检修项目招标明细"]
["分项","设备\n编号","项目名称","项目主要内容","增值税专票税率（%）","含税维修报价（万元）"]
[]
[1,51.01,"预热器维修（一）","1.更换C5A/B两台翻板锁风阀整体。（含吊装）"]
[2,56.01,"回转窑维修（一）","1.窑头密封摩擦片更换"]
[{"$nulls":3},"2.更换一档南侧拖轮（表面压溃）"]
[{"$nulls":3},"3.更换窑尾位置1#台轮带垫板；"]
[{"$nulls":3},"4.更换窑尾位置3#台轮带垫板；车轮带斜面，大齿圈对口调定、螺栓更换，大齿圈挡油环修复；更换弹簧板三件，固焊；窑中心线测定调整、调窑；\n"]
[{"$nulls":3},"5.更换液压挡轮，挡轮底座丝孔修复、加固；"]
[3,57.02,"推动棒式\n冷却机维修（一）","1.床面铸件全部拆除，更换部分磨损固定棒（总144）、推动棒（总144）、定位器（总288*2）、全部斜铁（1152）（每周期耐热铸件视磨损更换1/3左右）"]
[{"$nulls":3},"2.更换部分磨损低能篦板（总1344+80）、蓖板护板（总672）、U型栓板（总576）、入口的8根入口U型板（每周期耐磨件视磨损更换1/3左右，低能篦板100件左右）"]
[{"$nulls":3},"3.底部线轴承底座检查紧固、驱动板位置校正，连接板更换、紧固，更换全部的滑轨胶垫、单点润滑器更换电池,油杯（共96组），滑轨润滑油道疏通；"]
[{"$nulls":3},"4.更换8台液压缸，并调整24个液压缸的活塞杆长度，使每趟活塞杆长度一致\n（质保期1年，更换周期1年，每周期视磨损泄露情况更换全部的1/4，偶有增减）"]
[{"$nulls":3},"5.更换液压站滤芯、更换油站部分高压油管，渗漏的球阀、测压点漏油处理，高压管接头部分更换，氮气囊压力检查；"]
[{"$nulls":3},"6.尾端破碎机壳体两侧密封环压紧弹簧复位，减速机检查、处理密封"]
[4,57.02,"推动棒式\n冷却机维修（二）","1.更换9台冷却风机轴承箱为窜水轴承箱，更换全部轴承，窜水管路铺设（含保温）；进口百叶阀修整；风机壳体防锈补漆"]
[5,65.01,"熟料输送机技措","1.更换全部槽式料斗为后搭接料斗，更换链条，更换全部上下轨道、支架调整加固、打磨防锈刷漆"]
[{"$nulls":3},"2.更换斜拉链头轮轮毂，头部齿块更换，两端轴承清洗检测，输出轴联轴器尼龙棒更换；"]
[{"$nulls":3},"3.头部壳体、下料溜子修补，三处插板阀更换阀板"]
[{"$nulls":3},"4.尾轮两端更换轴承\n"]
[{"$nulls":3},"5.更换尾部活动导轨以及导轨托架\n"]
[{"$nulls":3},"6.安装头、尾防尘罩40米，头部收尘器风管按照新防尘罩改造"]
[{"$nulls":3},"7.尾部破碎机下料溜子改造，垂直部分改为前倾溜口，内部挡料格修补"]
[6,73.03,"辊盘式\n磨煤机维修（一）","1.更换11件磨盘瓦、3件辊套"]
[{"$nulls":3},"2.检查3组磨辊轴承，更换1#磨辊轴承；"]
[{"$nulls":3},"3.更换拉杆、更换上下关节轴承及下部密封总成"]
[{"$nulls":3},"4.分离器转子、连接桶检查，驱动部分检查，轴承清洗，密封更换"]
[{"$nulls":3},"5.找正三角框架，更换限位板、磨辊连接件，三脚架找正"]
[{"$nulls":3},"6.喷口环检查更换，堆焊磨内壳体磨损部位"]
[{"$nulls":3},"7.检查1、2、3#张紧液压缸，氮气囊检查更换"]
[{"$nulls":3},"8.吐渣仓刮料板更换"]
[{"$nulls":3},"9.修补磨机出口、入口膨胀节、连接管路"]
[{"$nulls":3},"10.选粉机静叶片在磨机出口部分更换"]
[{"$nulls":3},"11.磨机壳体清理，防锈刷漆"]
[{"$nulls":3},"12.施工所需脚手架拆搭"]
[{"$nulls":3},"13.更换地坑润滑液压站磨损液压件、密封件，打磨主过滤器上盖、攻丝，做密封；油站、管路外壁打磨清理，防锈刷漆；"]
[7,null,"窑头沉降室维修 （一）","1.窑头4楼沉降室进口管道自楼面两米至出口膨胀节部分整体更换包含两膨胀节；上部天圆地方壳体更换，内部导流板挖补；出口管道膨胀节至发电锅炉圆形管道挖补；入煤磨管道挖补；含管道保温拆除恢复；"]
[{"$nulls":3},"2.沉降室四立面壳体保温拆除恢复、壳体大面积挖补，内部导流板修整、挖补固焊；"]
[{"$nulls":3},"3.含搭拆脚手架、吊装费"]
[{"$nulls":3},"4.更换窑头3楼57.20篦冷机入沉降室主风管道阀门。"]
[8,41.06,"立磨维修（一）","1、辊套在线堆焊，计划6吨，磨盘在线堆焊计划1吨（按每公斤堆焊单价报价，计量焊丝量决算）"]
[9,41.06,"立磨维修（二）","2、41.05至立磨内部的下料溜子挖补（7.5㎡）、内铺设耐磨板，加水泥磨旧衬板"]
[{"$nulls":3},"3、下锥体支撑梁加固、做耐磨防护；"]
[{"$nulls":3},"4、更换撒料环、支撑环、坝环；铠甲板、铠甲板盖板，喷口环部分更换、修复；"]
[{"$nulls":3},"5、磨机内壳体衬板下半部部分更换"]
[{"$nulls":3},"6、磨辊护套修补（钟型、扇形）"]
[{"$nulls":3},"7、磨盘中心护板更换"]
[{"$nulls":3},"8、选粉机更换下轴承座、轴承及油封（6248M）"]
[{"$nulls":3},"9、更换喷水管、磨机壳体漏点补焊，4个磨门用耐磨板修补"]
[{"$nulls":3},"10、更换刮料装置，顶杠维修和更换.更换刮料板支架下部清扫刮板，刮料板支架下部焊口全部从新焊接。修补刮料装置与磨盘链接法兰；\n(易损，每年一次)"]
[{"$nulls":3},"11、吐渣仓内部壳体耐磨板衬圈修补，吐渣下料溜子挖补同时贴耐磨板。"]
[{"$nulls":3},"12、4个磨辊门挖补，同时用耐磨板修补（约8㎡）"]
[{"$nulls":3},"13、更换摇臂外部胶带（胶带自扒）密封胶板、胶块及摇臂密封衬板4套（每套10块衬板，含三角形衬板）"]
[{"$nulls":3},"14、氮气囊（32个）及活塞式蓄（16）能器检查氮气，更换4个氮气囊总成，活塞蓄能器2个\n"]
[{"$nulls":3},"15、出口膨胀节修补，更换蒙皮"]
[{"$nulls":3},"16、出料锁风阀更换"]
[{"$nulls":3},"17、磨辊螺栓护套部分更换约20个（厚壁管现场制作）"]
[{"$nulls":3},"18、更换3#/4#磨辊张紧液压缸"]
[{"$nulls":3},"19、4103气动三通分料阀内部挖补。"]
[{"$nulls":3},"20、4105回转下料器衬板更换，调整板更换"]
[{"$nulls":3},"21、4110气动三通分料阀壳体挖补，阀板轴加固（650X800角度50）"]
[10,41.06,"立磨维修（三）","22、减速机更齿轮箱体、上端盖，其他部位视拆检情况选择性更换"]
[11,"41.25/\n54.01","原料磨风机/高温风机维修","1、转子动平衡"]
[{"$nulls":3},"2、转子检查、磨损部分耐磨补焊，风机轴承检查"]
[{"$nulls":3},"3、入风管道及壳及循环风机壳体衬板堆焊修补"]
[{"$nulls":3},"4、循环风机法兰磨损处维修"]
[{"$nulls":3},"5、更换转子轴头密封"]
[{"$nulls":3},"6、循环风机喇叭口螺栓检查维修"]
[12,42.01,"\n钢丝胶带斗式提升机维修","1、更换钢丝胶带，重做接头，料斗利旧；"]
[{"$nulls":3},"2、检查减速机、逆止器、超越离合器，检查磁力耦合器"]
[{"$nulls":3},"3、上托轴承检查、注油，下托轴承检查更换、注油"]
[13,23.03,"侧取维修","1、头尾滑轮轴承检查、钢丝绳检查更换，头部齿块更换"]
[{"$nulls":3},"2、更换全部刮板（88块）刮板耐磨板、耙齿（704）"]
[{"$nulls":3},"3、导向轮（88件）更换"]
[{"$nulls":3},"4、上链条耐磨条更换"]
[{"$nulls":3},"5、下链条轨道盒更换"]
[14,84.13,"84.13辊压机：CLF170-100","1、更换辊压机动、定辊减速机。"]
[{"$nulls":3},"2、更换动辊大头内侧轴承密封"]
[{"$nulls":3},"2、双进料装置用耐磨板修补。"]
[{"$nulls":3},"3、更换侧挡板、检查维护棒阀、气动阀。"]
[{"$nulls":3},"4、修补辊压机下部溜子、壳体修复。"]
[{"$nulls":3},"5、检查更换减速机油管、水管。"]
[{"$nulls":3},"6、稳流仓至辊压机溜子用耐磨板补焊。"]
[15,84.14,"84.14辊压机：CLF170-100","1、更换辊压机定辊。"]
[{"$nulls":3},"2、双进料装置、入辊压机溜子拆装。"]
[{"$nulls":3},"3、双进料装置用耐磨板修补。"]
[{"$nulls":3},"5、修补辊压机下部溜子、壳体修复。"]
[{"$nulls":3},"6、稳流仓至辊压机溜子用耐磨板补焊。"]
[{"$nulls":3},"7、检查更换减速机油管、水管。"]
[{"$nulls":3},"8、挡料圈检查修复。"]
[16,84.31,"84.31水泥磨：Φ4.2*13m","1、磨头、磨尾滑履瓦座更换、研磨。"]
[{"$nulls":3},"2、拆卸安装前后滑履罩更换人字密封。"]
[{"$nulls":3},"3、入磨溜子、排渣溜子及固体流量计检查修补。"]
[{"$nulls":3},"4、检查更换油管、串水管。"]
[{"$nulls":3},"5、漏油点密封处理"]
[17,84.32,"84.32水泥磨：Φ4.2*13m","1、更换一室阶梯衬板。"]
[{"$nulls":3},"2、入磨溜子、排渣溜子及固体流量计检查修补。"]
[{"$nulls":3},"3、检查更换油管、串水管。"]
[{"$nulls":3},"4、漏油点密封处理"]
[18,null,"矿渣粉提升机","1、提升机下料点制作安装两个三通溜子，加一节斜槽2.5m，电气设备安装，电缆布线等。"]
[{"$nulls":3},"2、检查更换部分提升机斗子。"]
[19,null,"装运提升机","1、更换89.01提升机链条，检查更换料斗，检查更换轴承、加油"]
[{"$nulls":3},"2、更换86.53提升机链条，检查更换料斗，检查更换偶合器弹性盘、减速机，检查更换轴承、加油"]
[20,null,"发电冷水塔","1、更换出水管及花洒头"]